## Training
Topic | Sub Topic | Duration(Days) | Due Date | Owner | Status | Comments
General | AIS basic training | 1.5 |  | Self Learning | Completed
General | RCM basic training | 2.5 |  | Self Learning | Completed
General | Actimize products\groups overview | 0.1 |  | Session (Ran) | Not Started
Team (General) | Internal Products – High Level | 0.1 |  | Session (Ran) | Not Started
RCM Installation | RCM Installation for AAF | 0.5 |  | Self Installation | Not Started
Team (Automation) | AAF Installation | 0.5 |  | Self Learning | Completed
Team (Automation) | AAF training | 0.5 |  | Self Learning - AAF Training | In Progress
Team (Automation) | Code base | 0.1 |  | Session (Tomer) | Not Started
Team (Automation) | AAF development practices and guidelines (including Jenkins instructions) |  |  | Session (Tomer & Miri) | Not Started
Team (Automation) | 1st task: Self environment execution (Export Data) |  |  | Self (Tomer) | Not Started
Source control – GIT | Methodology overview | 0.1 |  | Session (Ran) | Not Started
Source control – GIT | Training Session |  |  | Self Learning | In Progress
Java | Differences between C# and Java | 0.2 |  | Small reference doc for diffs | Completed
Railways | Overview | 0.1 |  | Self Learning | Not Started
Operational tools | Tracker, NetApp, Jenkins, Artifactory | 0.1 |  | Session (Ran) | Not Started
Development methodology | SAFe, PIs, Iterations, etc. | 0.1 |  | Session (Ran) | Not Started